## Basic Manual Gantt Chart
Task Name | Start Date | End Date | Duration | Start Date in Number Form | 42576 | Use this number for the Minimum Bound of the Horizontal Axis to set the beginning of the chart.
Task One | 2016-07-25 | 2016-07-30 | 5
Task Two | 2016-07-27 | 2016-08-01 | 5
Task Three | 2016-07-27 | 2016-08-04 | 8
Task Four | 2016-07-27 | 2016-08-06 | 10
Task Five | 2016-08-01 | 2016-08-09 | 8
Task Six | 2016-08-01 | 2016-08-05 | 4
Task Seven | 2016-08-03 | 2016-08-10 | 7
Task Eight | 2016-08-05 | 2016-08-12 | 7
Task Nine | 2016-08-06 | 2016-08-09 | 3
Task Ten | 2016-08-06 | 2016-08-10 | 4
Task Eleven | 2016-08-07 | 2016-08-13 | 6
Task Twelve | 2016-08-10 | 2016-08-16 | 6
Task Thirteen | 2016-08-14 | 2016-08-19 | 5
Task Fourteen | 2016-08-15 | 2016-08-23 | 8
Task Fifteen | 2016-08-16 | 2016-08-26 | 10
Task Sixteen | 2016-08-17 | 2016-08-28 | 11
Task Seventeen | 2016-08-18 | 2016-08-29 | 11
|  |  |  | Key: | Calculated Cell |  | Manual Entry Cell
[5 empty] | These cells will be automatically calculated based on the inputs on other cells. |  | These cells require manual input so the calculated cells have data to work with.

## Gantt Chart - Manual Duration
Task Name | Start Date | End Date | Duration (Days) | Days Complete | Days Remaining | Percent Complete | Start Date in Number Form | 43133 | Use this number for the Minimum Bound of the Horizontal Axis to set the beginning of the chart.
Create Soul-Forge Git Repository | 2018-02-02 | 2018-02-03 | 1 | 1 | 0 | 100%
Implement Basic Level | 2018-02-03 | 2018-02-10 | 7 | 7 | 0 | 100%
Implement Basic Enemy | 2018-02-03 | 2018-02-10 | 7 | 7 | 0 | 100%
Implement Basic Hero and Weapons | 2018-02-03 | 2018-02-10 | 7 | 7 | 0 | 100%
Add Initial Sprites and Artwork | 2018-02-03 | 2018-02-10 | 7 | 7 | 0 | 100%
Create Collision Between Enemy/Hero/Level | 2018-02-09 | 2018-02-16 | 7 | 7 | 0 | 100%
Create Complete Level | 2018-02-10 | 2018-02-26 | 16 | 16 | 0 | 100%
Add most Weapons | 2018-02-10 | 2018-02-26 | 16 | 16 | 0 | 100%
Create tilesets and Sprites for items | 2018-02-10 | 2018-02-26 | 16 | 16 | 0 | 100%
Basic Enemy AI | 2018-02-10 | 2018-02-26 | 16 | 16 | 0 | 100%
Advanced Enemy AI | 2018-02-26 | 2018-03-23 | 25 | 0 | 25 | 0%
Add Second Basic Level | 2018-02-26 | 2018-03-23 | 25 | 0 | 25 | 0%
Menu and HUD | 2018-02-26 | 2018-03-23 | 25 | 0 | 25 | 0%
ALPHA
Finish Levels | 2018-03-23 | 2018-04-11 | 19 | 0 | 19 | 0%
Finish Enemies (AI, Art, Collision) | 2018-03-23 | 2018-04-11 | 19 | 0 | 19 | 0%
Finish Hero Mechanics | 2018-03-23 | 2018-04-11 | 19 | 0 | 19 | 0%
BETA DELIVERY
Extra Time for Polishing up Game | 2018-04-11 | 2018-04-23 | 12 | 0 | 12 | 0%
Final Debugging and Playtesting | 2018-04-11 | 2018-04-23 | 12 | 0 | 12 | 0%
Soul-Forge Completion | 2018-04-11 | 2018-04-23 | 12 | 7.5 | 4.5 | 62.5%
[7 empty] | Key: | Calculated Cell |  | Manual Entry Cell
[8 empty] | These cells will be automatically calculated based on the inputs on other cells. |  | These cells require manual input so the calculated cells have data to work with.